## Slide 1
SBSC Consulting Services - Confidential
Weekly Project Status Report
Development Team – SBSC Nigeria
Week 3, Friday 18th January, 2019

## Slide 2
TABLE OF CONTENTS
Presentation
Project Report – Ongoing Projects
Application Testing Report
Project Support Report
SBSC Consulting Services - Confidential

## Slide 3
Project Report – Ongoing Projects
SBSC Nigeria– Project Team Reports
Project Name | Team | Status | Weeks Achievement | Plans for next week | Issues | Owner | Mitigation plan
FCAAL | Back End Devs: Kenny, Ife, Kunle Front End Devs: Mitchell, John Paul Mobile Dev: Dayo Design: Samuel I PM: Idris Testers: Lamide, Mayowa | Sign-Off | Concluded UAT | Create and manage excel template containing all project details. | FCAAL asked for change in collateral release ui and worklflow FCAAL asked for bi-weekly DRA report Mobile developer needs a mac to test ios version | Development Team Mobile Dev | Weekend work to finish up in time for Tuesday Weekend work to finish up in time for tuesday Dayo has to come this weekend to use sams system
Mini JOE | Back End Devs: Mariam, Wole Front End Devs : Wale Design: Jude PM: Idris | Development | Integrated given GOPD And immunization screens | Completion of immunization integration screens. GOPD and Imumunization code clean up. GAP analytics on JOE and Mini JOE |  |  | 
LMS | Back End Devs: John Paul, Kenny, Samuel B Front End Devs : Mitchell Design: Samuel I PM: Idris | Support | •Change SCORM delivery logic by using a proxy to a CDN to improve content loading and delivery time. (100%) – Currently testing •Meeting with sterling on a need to improve the application UI/UX •Meeting with Sterling on HC HUB and LMS integration, integration test is being carried out | •Test live classroom at Sterling. •Begin internal regression test •Meet with Sterling branding team to gather new UI requirements •Fix issues that may arise after integration testing •Deploy SCORM-CDN to live environment |  |  | 
First Bank | Back End Devs: Samuel | Requirements Sign-off | •Created the project and necessary database entities | •Read through requirements document and architect the project •Kickstart project development |  |  | 

## Slide 4
Project Report – Ongoing Projects
SBSC Nigeria– Project Team Reports
Project Name | Team | Status | Weeks Achievement | Plans for next week | Issues | Owner | Mitigation plan
Oando | Back End Devs: Kenny Front End Devs: Wale Design: Jude, Samuel I PM: Idris | Project Kick-Off |  |  |  |  | 

## Slide 5
Project Report – Departmental Goals
SBSC Nigeria– Project Team Reports
Goal | Measures | Assigned Owner | Current Status | Week’s Target | Week’s Achievement | Next Steps
Project Inventory/Documentation | Create central repository to hold all project details for easy access | Kehinde Adewale | In Progress | Create and manage excel template containing all project details. | Google sheet created https://docs.google.com/spreadsheets/d/1ga3vWtftqj-VrG7HAeGQyE-KQHmRpb2mglM3_PvOXYQ/edit?usp=sharing​​ | Set up open source tool and migrate data. Move all project documents to application.
Improve Delivery | Create backend web template Create frontend web template | Kehinde Adewale, Samuel Babalola Samuel O, Wale Adebowale | Not Started Not Started | Team briefed on the neeed to create reusable templates and plan to begin next week |  | Implementation
Service Delivery | Create SBSC support email Create central database to save all system errors | Kehinde Adewale Samuel Babalola | Not Started Not Started |  |  | Route all application escalated support tickets to sbsc Nigeria support mail
Knowledge Sharing | An hour SBSC Innovation meeting to hold bi-weekly on Fridays at 8am | Kehinde Adewale | Planning | Brief team on intended schedule and plan |  | Schedule staff to take sessions for first quater of the year

## Slide 6
Project Support Report
SBSC Nigeria– Project Team Reports
Project Name | Support Lead | Support Status | Number of Issues Raised | Issues Closure Update | Critical Issues Raised | Mitigation Plan