## Sheet1
Project Name | Project Owner / Lead Developer | Delivery Milestone | %Complete | Proposed Finish Date | Status | Key Achievements | Plans for Next Period | Risk/Issues | Mitigation Plan
SBSC Recuitment Software | Shontan Kayode / SBSC Nigeria Interns | Functional Requirement Gathering | 95% | 16th Nov. 2018 | Signed the FRD. Given the application requirements to the UI Designer | None | Corrections pending and yet to be solved. -Stakeholder Document to be sent for sign-off. -UI screens in Progress. | Late Response of UI Screens. Priority Given to Other Projects.
|  | Application Design | 15% | 30th Nov. 2018 | Designing UI Screens | None
|  | Environment Framework Development | 50% | 14th Dec. 2018 | Application Background Development | None
|  | Admin Module Dev. | 10% | 4th Jan. 2019 | None | None
|  | Applicant Module Dev. | 0% | 18th Jan. 2019 | None | None
|  | Application Testing (Functionality Testing, Performance Testing, Security Testing, UAT ) | 5% | 25th Jan. 2019 | Studing the FRD. Gathering the Application Requirements to prepare Functionality Testing | None |  | None | None
|  | Go Live | 0% | 31st Jan. 2019 | None | None |  | None | None
|  | Support | 0% | None | None | None |  | None | None